## P&R Action Items
Action Item # | Status | Description | Action Lead | Target Due Date | Notes
1 | Open | Aunt Caroline’s Park fountain: Recommendation and estimates for what to do with broken fountain. | Paul |  | Concensus seems to be to make the fountain a planter since clean water to the site will be problematic. Paul/Spencer looking into moving fountain to a better site and pouring a new footer. Effort still in investigative stage. Another option is to abandon the fountain.
2 | Open | Flag Program: Advertise/get Flag program coordinator and maintenance team. | Kathy |  | Approval granted to buy 50 daffodil flags for spring ($780). The flags have been ordered. Work to continue to use the remaining membership funds to buy new summer flags since these will be largely unusable next year. Final vote for bridge flag designs has taken place. Once flag inventory is settled, we can focus on getting a Flag program coordinator.
3 | Open- On Hold | Event Handbook: Continue work to complete. |  |  | Kathy did a rework; Betty provided revisions. Per Tom, insurance near term will prevent us from renting out any park facilities except the Riverhouse. We will need to strip out all non-Riverhouse park rental language. The barebones handbook should simply contain: key checkout for Aunt Caroline's bathroom, Riverhouse, and possibly some language on use of the parks for festivals. This will essentially be a rewrite of the Event Handbook. As we grow, we will add back in the stripped out material as appropriate. As of 10/1 the handbook is mostly done.
4 | Open- On Hold | Next revision of Riverhouse App: Rework terms and establish new fees for Riverhouse and parking lot. |  |  | See #3 above re: incorporation into Event Handbook. Also need to establish new pricing. Bonnie provided sample venue pricing for consideration in establishing Riverhouse rental prices. Per Tom, current insurance will not allow us to charge for parking so it will need to be free for the foreseeable future. Waiting for final approval.
5 | Closed | Music in the Park: Invite Sue Krupa to next meeting. | Kathy | 2019-10-01 | Sue Krupka attended the 10/1 Park meeting. She gave lots of info on the logistics of operating Music in the Park
6 | Open | Per Hank at City Council: Think about establishing Shady Cove as a City of Festivals | commission |  | Talked about starting with 2 festivals: June and late September to frame summer. The June festival should include the Watershed's Festival on the Rogue. We can explore the possibility of a beer garden at Riverhouse.
7 | Closed | Aunt Caroline’s Park river bank: Restoration | Tom & Spencer |  | Restoration activities are underway and scheduled. As of late October restoration is near completion.
8 | Closed | Aunt Caroline's Park ADA ramp | Tom & Spencer | 2019-09-03 | The ADA ramp has been completed
9 | Open- On Hold | Upper Rogue Regional Park boat ramp | Tom |  | Design was done years ago; Marine board will do the work. Since they are paying, we should let them take the lead. Chuck (coordinator of Festival on the Rogue) voiced concern over the plans calling for the removal of 16 trees. City to see if those 16 trees are all still there. Also, trees must be removed for expansion of ramp ingres/egres.
| Open |  |  |  | There was a plan done by the county years ago. This needs to be reviewed and updated with future plans
10 | On Hold | Update Park Masterplan | Tom
Do we need to follow county masterplan rules?
|  | Revise Riverhouse Logo | Tom |  | The city's website designer will work on it. The new logo will be presented on 11/2
11 | Open-On
Hold
|  | Educational Signage on Fence | Watershed |  | Possible the Watershed Council will work with our commission to agree on signage
12 | Open |  | Council
|  | Aunt Caroline's Park- Sprinklers to be fixed with automatic timers |  | 2019-09-03
13 | Closed |  | Tom
|  |  | Tom | 2019-09-03 | Tom is working with a volunteer who will trap and transport cats
14 | Closed | Aunt Caroline's Park- Stray cats to be trapped and spayed or neutered
|  |  | Tom |  | Arrangements to be made to work with school to facilitate planting
15 | Closed | Aunt Caroline's Park - Bank Restoration - Planting |  | 2019-10-18
16 | Open | Aunt Caroline's dog walk park- to be finished in Spring | Tom
17 | Open | Electrical Box at Aunt Caroline's upgraded to all-weather | Tom
18 | Open | Metal Sign for Aunt Caroline's to be installed | Tom
19 | Open | Bid requests put out for stairs and food truck slabs | Tom
20 | Open | Finalize amount and present city council with Music in the Park Budget | Tom
21 | Open | Finalize date of and finalize plans for celebration of City's birthday during | commission
Music in the Park
22 | Open | Redesign Music in the Park Flyers | Commission
23 | Open | Invite Hank to present specific ideas on how he would like the commission | Commission
to help with the Woodworking Festival
24 | Open | Discuss holding a workshop to discuss branding ideas/at least 2 hours | Commission
Informally collect ideas from anyone interested
Restrict workshop to commission and city adminstrator
25 | Open | Follow-up on community calendar and electronic sign | Tom